PROJECT DOCUMENTATION REPORT

3. PROJECT PLANNING PHASE

Work Breakdown, Schedule, Resource & Risk Management Plan

| Project Title | AUTOMATING EMPLOYEE DATA |
| --- | --- |
| Course | SALESFORCE |
| Academic Year | 2025 – 2026 ¦ Six Semester |
| Group / Team No. | Group / 5 |
| Submission Date | March 09, 2026 |
| Document Version | v1.0 — Initial Release |

3.1  Introduction

The Project Planning Phase constitutes the third stage of the Software Development Life Cycle (SDLC) and represents the formal transition from requirements documentation to actionable project execution. During this phase, the project team establishes the structural and managerial framework required to guide the development effort through its remaining phases in an organized, resource-efficient, and time-bound manner.

Effective project planning is essential for the successful delivery of any software project. It ensures that all team members have a shared understanding of project scope, individual responsibilities, delivery milestones, and risk mitigation strategies. This document presents the comprehensive planning artifacts produced for the Student Information Management System (SIMS), including the project scope statement, work breakdown structure, project schedule, resource plan, risk management plan, communication plan, and quality assurance plan.

3.2  Project Scope Statement

The project scope defines the boundaries of the work to be performed during the current project cycle. It establishes a clear mutual understanding between the project team and stakeholders regarding what is included in and excluded from the system to be developed.

3.2.1  In-Scope Deliverables

The following deliverables are formally included within the scope of this project:

- Phase documentation reports for all SDLC phases: Identification, Requirements Analysis, Project Planning, System Design, Development, Testing, and Deployment.

- A fully functional web-based Student Information Management System encompassing all modules defined in the approved requirements specification.

- A relational database schema and populated database for managing student, faculty, course, enrollment, and grade data.

- A role-based user management system supporting Administrator, Faculty, and Student access levels.

- An automated academic report generation module with PDF and Excel export capabilities.

- A user manual and technical documentation package for system administrators and end users.

- A structured user acceptance testing (UAT) report verifying compliance with approved functional and non-functional requirements.

3.2.2  Out-of-Scope Items

The following items are explicitly excluded from the current project scope and deferred for future phases:

- Integration with third-party Learning Management Systems (LMS) or external academic platforms.

- Financial transaction processing, billing, and fee management functionality.

- Development of a dedicated native mobile application for iOS or Android platforms.

- Public-facing internet portal accessible outside the institution's network environment.

- Automated synchronization with government or national student registry databases.

3.3  Project Team Roles and Responsibilities

The project is undertaken by a multidisciplinary team composed of students enrolled in the Software Engineering course. Each member has been assigned a primary role aligned with their competencies, with the understanding that collaborative support across roles is expected throughout the project lifecycle.

| Member No. | Assigned Role | Primary Module | Key Responsibilities |
| --- | --- | --- | --- |
| Member 1 | Project Manager | All Phases | Project coordination, schedule management, stakeholder communication, risk monitoring, and documentation oversight. |
| Member 2 | Systems Analyst | Requirements & Design | Requirements elicitation, use case development, data flow modeling, and system architecture documentation. |
| Member 3 | Lead Developer | Back-End Development | Server-side logic, database design and implementation, API development, and system integration. |
| Member 4 | Front-End Developer | UI/UX Development | User interface design, client-side scripting, responsive layout development, and usability optimization. |
| Member 5 | QA Lead | Testing & Validation | Test plan development, functional and non-functional testing, defect tracking, UAT facilitation, and test reports. |
| Member 6 | Documentation Officer | All Phases | Preparation and formatting of all phase documentation reports, meeting minutes, and submission packages. |

3.4  Work Breakdown Structure (WBS)

The Work Breakdown Structure decomposes the total project scope into manageable work packages organized hierarchically by project phase. Each work package is assigned a unique WBS identifier for tracking and reporting purposes.

| WBS ID | Phase / Work Package | Key Deliverables | Responsible Member(s) |
| --- | --- | --- | --- |
| 1.0 | Identification Phase | Problem statement, feasibility study, stakeholder identification report | All Members |
| 1.1 | Problem Definition | Problem statement document, initial scope boundaries | Member 1, 2 |
| 1.2 | Stakeholder Analysis | Stakeholder register, interest-influence matrix | Member 2 |
| 1.3 | Feasibility Study | Technical, operational, economic, schedule feasibility report | Member 1, 2 |
| 2.0 | Requirements Analysis | Functional & non-functional requirements specification, use case catalog | Member 2, 5 |
| 2.1 | Requirements Elicitation | Interview notes, survey results, observation records | Member 2 |
| 2.2 | FR & NFR Documentation | 22 functional & 12 non-functional requirements with acceptance criteria | Member 2, 5 |
| 2.3 | Requirements Validation | Validated requirements, stakeholder sign-off records | All Members |
| 3.0 | Project Planning | WBS, Gantt chart, risk register, resource plan, communication plan | Member 1 |
| 3.1 | Schedule Development | 18-week Gantt chart, milestone register | Member 1 |
| 3.2 | Resource Planning | Resource allocation matrix, hardware and software inventory | Member 1, 3 |
| 3.3 | Risk Management Plan | Risk register, probability-impact matrix, mitigation strategies | Member 1 |
| 4.0 | System Design | ERD, DFD, system architecture diagrams, UI wireframes, database schema | Member 2, 3, 4 |
| 4.1 | Database Design (ERD) | Entity-relationship diagram, normalized schema | Member 3 |
| 4.2 | System Architecture | Layered architecture diagram, component and deployment views | Member 2, 3 |
| 4.3 | UI/UX Wireframes | High-fidelity prototype screens for all system modules | Member 4 |
| 5.0 | System Development | Source code, database scripts, integration builds, code review logs | Member 3, 4 |
| 5.1 | Database Implementation | MySQL schema scripts, seed data, migrations | Member 3 |
| 5.2 | Back-End Development | Laravel API, authentication module, business logic layers | Member 3 |
| 5.3 | Front-End Development | React.js UI components, responsive layouts, client-side validation | Member 4 |
| 5.4 | System Integration | End-to-end integration of all modules, API testing | Member 3, 4 |
| 6.0 | Testing & QA | Test cases, defect log, UAT report, performance test results | Member 5, All |
| 6.1 | Unit & Integration Testing | Test case results, defect tracking log | Member 5 |
| 6.2 | User Acceptance Testing | UAT scenarios, sign-off forms, final test report | Member 5, All |
| 7.0 | Deployment & Closeout | Deployed system, user manual, final project report, oral defense | All Members |
| 7.1 | System Deployment | Live system on production server, deployment documentation | Member 3, IT Dept. |
| 7.2 | Documentation & Training | User manual, admin guide, training session delivery | Member 6, All |
| 7.3 | Final Presentation & Submission | Oral defense presentation, complete project portfolio submission | All Members |

3.5  Project Schedule

The project schedule spans eighteen (18) weeks covering the complete academic semester. The schedule was developed using the Critical Path Method (CPM) to identify task dependencies and ensure that milestone deadlines are achievable within the allocated timeframe. The Gantt chart below presents the planned timeline for all major project work packages.

3.5.1  Project Milestones

| MS ID | Milestone Description | Target Week | Responsible |
| --- | --- | --- | --- |
| MS-01 | Project Kick-off and Scope Approval | Week 1 | Member 1 |
| MS-02 | Identification Phase Documentation Submitted | Week 2 | Member 1, 2 |
| MS-03 | Requirements Analysis Documentation Submitted | Week 4 | Member 2, 5 |
| MS-04 | Project Planning Documentation Submitted | Week 5 | Member 1 |
| MS-05 | System Design Documentation Submitted | Week 8 | Member 2, 3, 4 |
| MS-06 | Development Phase Completion (Code Freeze) | Week 14 | Member 3, 4 |
| MS-07 | User Acceptance Testing (UAT) Completed | Week 16 | Member 5 |
| MS-08 | System Deployment and Final Submission | Week 18 | All Members |

3.5.2  Gantt Chart — 18-Week Project Schedule

| ID | Work Package / Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Identification Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Problem Definition | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Stakeholder Analysis | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | Feasibility Study |  | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.0 | Requirements Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Requirements Elicitation |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | FR & NFR Documentation |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Requirements Validation |  |  |  | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.0 | Project Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Schedule Development |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Resource Planning |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 | Risk Management Plan |  |  |  |  | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.0 | System Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Database Design (ERD) |  |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 | System Architecture |  |  |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 | UI/UX Wireframes |  |  |  |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |
| 5.0 | System Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Database Implementation |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |
| 5.2 | Back-End Development |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ |  |  |  |  |  |  |
| 5.3 | Front-End Development |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ |  |  |  |  |  |
| 5.4 | System Integration |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |
| 6.0 | Testing & QA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Unit & Integration Testing |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |
| 6.2 | User Acceptance Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |
| 6.3 | Defect Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ |  |  |
| 7.0 | Deployment & Closeout |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 | System Deployment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |
| 7.2 | Documentation Finalization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ |  |
| 7.3 | Final Presentation & Submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ |

Legend:  ■ Active task week   |   Light blue shading = Phase duration span   |   Teal = Planning phase

3.6  Resource Management Plan

The resource management plan identifies and allocates the human, hardware, software, and financial resources required to execute the project plan. Effective resource management ensures that all project activities are adequately supported without unnecessary expenditure or team member overload.

3.6.1  Human Resource Allocation

| Team Member | Role | Ph.1 | Ph.2 | Ph.3 | Ph.4 | Ph.5-6 | Est. Total Hrs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Member 1 | Project Manager | High | Med | High | Med | Med | ~120 hrs |
| Member 2 | Systems Analyst | High | High | Med | High | Low | ~130 hrs |
| Member 3 | Lead Developer | Low | Low | Med | High | High | ~160 hrs |
| Member 4 | Front-End Developer | Low | Low | Low | High | High | ~140 hrs |
| Member 5 | QA Lead | Low | High | Low | Med | High | ~120 hrs |
| Member 6 | Documentation Officer | High | High | High | Med | High | ~110 hrs |

Note: High = primary contributor; Med = supporting role; Low = advisory or review only.

3.6.2  Technology Resource Requirements

| Category | Resource | Purpose | Availability |
| --- | --- | --- | --- |
| Hardware | Development Laptops (x6) | Individual coding, design, documentation, and testing workstations for each team member. | Team-owned |
| Hardware | Local Test Server | On-premise server for development environment hosting and integration testing. | Institution-provided |
| Software | PHP / Laravel Framework | Back-end application framework for server-side logic and API development. | Open-source |
| Software | React.js | Front-end JavaScript library for building the dynamic user interface layer. | Open-source |
| Software | MySQL Database | Relational database management system for structured data storage. | Open-source |
| Software | Visual Studio Code | Primary integrated development environment (IDE) for all coding activities. | Free / Open-source |
| Software | Git / GitHub | Version control system and remote repository for collaborative code management. | Free |
| Software | Figma | Collaborative UI/UX design and wireframing tool for interface prototyping. | Free (Student) |
| Collaboration | MS Teams / Discord | Team communication, virtual meetings, and file sharing platform. | Free |

3.7  Risk Management Plan

The risk management plan identifies potential threats to project success, assesses their likelihood and impact, assigns ownership, and prescribes mitigation and contingency strategies. Risks were identified through team brainstorming sessions and review of similar academic software engineering projects.

3.7.1  Risk Probability and Impact Scale

| Rating | Probability (P) | Impact (I) | Risk Score (P x I) |
| --- | --- | --- | --- |
| 1 — Very Low | < 10% likelihood | Negligible effect on project | 1 |
| 2 — Low | 10% – 30% likelihood | Minor delays or rework | 4 |
| 3 — Medium | 31% – 50% likelihood | Moderate schedule or quality impact | 9 |
| 4 — High | 51% – 75% likelihood | Significant milestone delays | 16 |
| 5 — Very High | > 75% likelihood | Critical failure or project termination | 25 |

3.7.2  Risk Register

| Risk ID | Risk Description | Prob. | Impact | Score | Owner | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Team member unavailability due to illness, academic conflicts, or withdrawal from the course. | 3 | 4 | 12 | Member 1 (PM) | Maintain cross-training on critical tasks; document all work for handover. Adjust schedule buffer weeks if needed. |
| R-02 | Scope creep resulting from uncontrolled addition of features beyond approved requirements. | 4 | 3 | 12 | Member 1, All | Enforce formal change request process; any new requirement must receive adviser approval before implementation. |
| R-03 | Technical integration failures between front-end, back-end, and database layers during system integration. | 3 | 4 | 12 | Member 3 (Dev) | Conduct integration testing incrementally at end of each sprint; establish API contracts early in design phase. |
| R-04 | Data loss or corruption due to absence of version control discipline or local storage failure. | 2 | 5 | 10 | Member 3, All | Mandate daily commits to GitHub; enforce branching strategy; maintain automated database backups on server. |
| R-05 | Schedule delays due to underestimation of development complexity or unforeseen technical obstacles. | 3 | 3 | 9 | Member 1 (PM) | Include two-week schedule buffer (Weeks 15-16) as contingency; conduct weekly progress reviews. |
| R-06 | Stakeholder unavailability for validation sessions, causing requirements or UAT delays. | 2 | 3 | 6 | Member 1, 6 | Schedule validation sessions at least two weeks in advance; prepare asynchronous validation alternatives. |
| R-07 | Technology stack incompatibilities or library deprecation affecting system functionality. | 2 | 3 | 6 | Member 3 (Dev) | Lock dependency versions in package manifest; test compatibility before updating any library or framework. |
| R-08 | Security vulnerabilities discovered during testing requiring significant rework before deployment. | 2 | 4 | 8 | Member 5 (QA) | Conduct security code reviews at end of each sprint; apply OWASP Top 10 guidelines throughout development. |

Risk Score Legend:  Score ≥ 10: High Risk (yellow highlight)    Score < 10: Moderate / Low Risk (green highlight)

3.8  Communication Management Plan

The communication plan defines the channels, frequency, format, and responsible parties for all project communications. Effective communication is critical to maintaining team alignment, managing stakeholder expectations, and ensuring timely escalation of issues.

| Communication Type | Audience | Channel | Frequency | Responsible Party |
| --- | --- | --- | --- | --- |
| Weekly Team Sync | Project Team | MS Teams / Discord | Weekly (Monday) | Project Manager (Member 1) |
| Progress Report | Adviser / Instructor | Email / LMS Portal | Bi-weekly | Documentation Officer (Member 6) |
| Phase Review Meeting | All Stakeholders | In-Person / Online | End of each phase | Project Manager (Member 1) |
| Task Status Updates | Project Team | GitHub Issues / Chat | Daily (async) | All Team Members |
| Issue Escalation | PM & Adviser | Email / Direct Message | As required | Relevant Team Member |
| Document Submission | Course Instructor | LMS Portal / Email | Per milestone date | Documentation Officer (Member 6) |
| Final Presentation | Panel / Instructor | In-Person (Classroom) | Week 18 | All Team Members |

3.9  Quality Assurance Plan

The quality assurance plan establishes the standards, processes, and review mechanisms the project team will employ to ensure that all project deliverables — both documentation and software artifacts — meet the defined acceptance criteria and stakeholder expectations.

3.9.1  Documentation Quality Standards

- All phase documentation shall be reviewed by at least two team members before submission to the project adviser.

- Documents must conform to the approved report template, including consistent heading styles, font usage, and section numbering conventions.

- All tables, diagrams, and figures must be clearly labelled and referenced in the accompanying narrative.

- Formal spelling and grammar review shall be conducted by the Documentation Officer prior to each submission.

3.9.2  Software Quality Standards

- All source code shall adhere to the team-agreed PHP PSR-12 and JavaScript ESLint coding standards.

- Code reviews are mandatory for all pull requests; no code shall be merged to the main branch without approval from at least one other developer.

- Unit tests shall achieve a minimum code coverage of 70% for all critical system modules prior to integration.

- All functional requirements (FR-001 to FR-022) must have corresponding test cases in the test plan, with documented pass or fail results.

- Security testing against the OWASP Top 10 vulnerability checklist shall be conducted prior to the user acceptance testing phase.

3.9.3  Quality Review Schedule

| Review Type | Scope | Scheduled At | Reviewer(s) |
| --- | --- | --- | --- |
| Peer Review | Each phase documentation report reviewed for completeness and accuracy. | Prior to each phase submission | Designated reviewer pair |
| Code Review | Review of all pull requests for code quality, security, and standards compliance. | Each development sprint | Lead Developer + 1 peer |
| Integration Test | End-to-end functional testing of integrated system modules against requirements. | Weeks 13 – 14 | QA Lead + Dev team |
| UAT Review | Formal acceptance testing with end-user participation validating all functional requirements. | Weeks 15 – 16 | QA Lead + Stakeholders |
| Final QA Audit | Comprehensive review of all deliverables against project scope and acceptance criteria. | Week 17 | All Members + Adviser |

3.10  Project Budget Estimate

As an academic project, the primary resource investment is the time contribution of team members. The following table presents the estimated project budget covering all anticipated direct costs associated with the development, testing, and deployment of the system.

| Item No. | Budget Item Description | Unit Cost | Quantity | Total (PHP) |
| --- | --- | --- | --- | --- |
| 1 | Web Hosting Service (shared hosting, 1-year subscription) | PHP 2,500.00 | 1 subscription | 2,500.00 |
| 2 | Domain Name Registration (.com, 1-year) | PHP 800.00 | 1 domain | 800.00 |
| 3 | SSL Certificate (if not bundled with hosting plan) | PHP 1,200.00 | 1 certificate | 1,200.00 |
| 4 | Printed Documentation and Binding (final submission copies x 2) | PHP 350.00 | 2 copies | 700.00 |
| 5 | Miscellaneous Supplies (printing, flash drives, presentation materials) | PHP 500.00 | Lump sum | 500.00 |
| 6 | Contingency Reserve (10% of total direct costs) | — | — | 570.00 |
| TOTAL ESTIMATED PROJECT BUDGET: |  |  |  | PHP 6,270.00 |

Note: All software tools and development frameworks are open-source or freely available under academic licenses, incurring no licensing costs.

3.11  Conclusion

The Project Planning Phase has produced a comprehensive and actionable set of planning documents that establish the structural foundation for the successful execution of the Student Information Management System (SIMS) development project. Through the development of the Work Breakdown Structure, 18-week Gantt schedule, resource allocation matrix, risk register, communication plan, quality assurance framework, and budget estimate, the project team has demonstrated thorough preparation for the challenges of the development phases ahead.

The planning artifacts presented herein reflect a realistic and well-considered approach to project management within the constraints of an academic semester. All identified risks have been assigned owners and mitigation strategies, and the project schedule incorporates contingency buffer weeks to accommodate unforeseen delays. Resource allocations have been calibrated to match each team member's primary expertise while distributing workload equitably across the project timeline.

The project team formally endorses the planning documents contained in this phase report and recommends progression to Phase 4: System Design, wherein the technical architecture, database schema, data flow models, and user interface prototypes for the SIMS shall be developed and documented in accordance with the approved requirements specification.

Prepared & Submitted By

| Project Leader: ________________________________ [Student Name] [Student ID] ¦ [Course & Year] | Approved By: ________________________________ [Instructor / Adviser Name] Subject Instructor |
| --- | --- |